## project-tasks-report
| Project | Task Name | Start Date | End Date | Assigned To | Cost | Budget | Status
| ACME Web Configuration | Identify server requirements | 2021-09-14 | 2021-10-12 | John Watson | 100 | 200 | Closed
| ACME Web Configuration | Determine Web listener configuration(s) | 2021-08-10 | 2021-08-18 | James Cassidy | 100 | 100 | Closed
| ACME Web Configuration | Specify security authentication scheme(s) | 2021-10-01 | 2021-10-05 | John Watson | 200 | 300 | Closed
| ACME Web Configuration | Select servers for Development, Test, Production | 2021-09-06 | 2021-09-08 | James Cassidy | 200 | 600 | Closed
| ACME Web Configuration | Configure Workspace provisioning | 2021-08-13 | 2021-08-29 | John Watson | 200 | 100 | Closed
| ACME Web Configuration | Create pilot workspace | 2021-10-08 | 2021-10-25 | John Watson | 100 | 100 | Closed
| ACME Web Configuration | Run installation | 2021-08-25 | 2021-09-18 | James Cassidy | 100 | 100 | Closed
| Bug Tracker | Implement bug tracking software | 2021-10-02 | 2021-10-05 | Myra Sutcliff | 100 | 100 | Closed
| Bug Tracker | Review automated testing tools | 2021-08-23 | 2021-09-05 | Myra Sutcliff | 2750 | 1500 | On-Hold
| Bug Tracker | Document quality assurance procedures | 2021-09-18 | 2021-10-07 | Myra Sutcliff | 3500 | 4000 | Open
| Bug Tracker | Train developers on tracking bugs | 2021-09-13 | 2021-09-19 | Myra Sutcliff | 0 | 2000 | On-Hold
| Bug Tracker | Measure effectiveness of improved QA | 2021-07-17 | 2021-07-18 | Myra Sutcliff | 500 | 1500 | Pending
| Client Server Conversion | Identify pilot client server applications | 2021-10-05 | 2021-10-09 | Scott Spencer | 200 | 200 | Closed
| Client Server Conversion | Migrate pilot client server to web | 2021-08-18 | 2021-09-12 | Scott Spencer | 400 | 500 | Closed
| Client Server Conversion | Post-migration review | 2021-09-11 | 2021-10-02 | Pam King | 100 | 100 | Closed
| Client Server Conversion | Plan migration schedule | 2021-10-07 | 2021-10-29 | Pam King | 100 | 100 | Closed
| Client Server Conversion | Migrate client server apps | 2021-07-20 | 2021-08-06 | Pam King | 300 | 12000 | Open
| Client Server Conversion | Test migrated applications | 2021-07-20 | 2021-08-06 | Russ Saunders | 0 | 6000 | Pending
| Client Server Conversion | User acceptance testing | 2021-10-08 | 2021-10-19 | Russ Saunders | 0 | 2500 | Pending
| Client Server Conversion | End-user Training | 2021-08-03 | 2021-08-30 | Myra Sutcliff | 0 | 2500 | Pending
| Client Server Conversion | Rollout migrated clent server apps on web | 2021-07-29 | 2021-08-26 | Pam King | 0 | 500 | Pending
| Convert Spreadsheet | Collect mission-critical spreadsheets | 2021-09-12 | 2021-10-11 | Pam King | 2500 | 4000 | Open
| Convert Spreadsheet | Send links to previous spreadsheet owners | 2021-08-07 | 2021-08-24 | Pam King | 1000 | 1500 | Open
| Convert Spreadsheet | Create web applications from spreadsheets | 2021-08-28 | 2021-09-09 | Pam King | 10000 | 6000 | Open
| Convert Spreadsheet | Lock spreadsheets | 2021-07-31 | 2021-08-16 | Pam King | 1000 | 800 | Open
| Discussion Forum | Install web application on production server | 2021-08-02 | 2021-08-28 | Hank Davis | 100 | 100 | Closed
| Discussion Forum | Monitor participation | 2021-09-07 | 2021-09-28 | Hank Davis | 450 | 500 | Open
| Discussion Forum | Identify owners | 2021-08-08 | 2021-09-03 | Hank Davis | 250 | 300 | Closed
| Email Integration | Get RFPs for new server | 2021-09-28 | 2021-10-11 | Mark Nile | 2000 | 1000 | Open
| Email Integration | Check software licenses | 2021-08-14 | 2021-08-16 | Mark Nile | 200 | 200 | Closed
| Email Integration | Purchase backup server | 2021-07-14 | 2021-08-12 | Mark Nile | 0 | 3000 | Pending
| Email Integration | Complete plan | 2021-08-11 | 2021-08-20 | Mark Nile | 3000 | 1500 | Closed
| Employee Satisfaction Survey | Review with legal | 2021-09-02 | 2021-10-01 | Irene Jones | 200 | 400 | On-Hold
| Employee Satisfaction Survey | Plan rollout schedule | 2021-07-13 | 2021-08-01 | Irene Jones | 0 | 750 | On-Hold
| Employee Satisfaction Survey | Complete questionnaire | 2021-07-22 | 2021-07-24 | Irene Jones | 1200 | 800 | On-Hold
| Load Packaged Applications | Install in development | 2021-07-16 | 2021-07-25 | John Watson | 100 | 100 | Closed
| Load Packaged Applications | Implement in Production | 2021-07-11 | 2021-07-19 | John Watson | 200 | 1500 | Open
| Load Packaged Applications | Identify point solutions required | 2021-09-10 | 2021-09-24 | John Watson | 200 | 300 | Closed
| Load Packaged Applications | Train developers / users | 2021-09-23 | 2021-10-20 | John Watson | 0 | 8000 | Pending
| Load Packaged Applications | Customize solutions | 2021-07-28 | 2021-08-03 | John Watson | 1500 | 4000 | Open
| Maintain Support Systems | HR software upgrades | 2021-08-12 | 2021-08-31 | Pam King | 8000 | 7000 | On-Hold
| Maintain Support Systems | Apply Billing System updates | 2021-09-09 | 2021-09-29 | Russ Sanders | 9500 | 7000 | On-Hold
| Maintain Support Systems | Investigate new Virus Protection software | 2021-08-25 | 2021-09-08 | Pam King | 1700 | 1500 | Open
| Maintain Support Systems | Arrange for vacation coverage | 2021-09-08 | 2021-09-17 | Al Bines | 300 | 500 | Open
| Migrate Desktop Application | Migrate Desktop Applications | 2021-07-21 | 2021-08-10 | Mark Nile | 1000 | 8000 | Open
| Migrate Desktop Application | Identify pilot applications | 2021-08-18 | 2021-09-12 | Mark Nile | 300 | 500 | Closed
| Migrate Desktop Application | User acceptance testing | 2021-07-28 | 2021-08-17 | Mark Nile | 1500 | 6000 | Open
| Migrate Desktop Application | Migrate pilot applications to web | 2021-07-21 | 2021-07-27 | Mark Nile | 500 | 500 | Closed
| Migrate Desktop Application | Post-migration review | 2021-10-02 | 2021-10-05 | Mark Nile | 100 | 100 | Closed
| Migrate Desktop Application | Plan migration schedule | 2021-08-06 | 2021-08-06 | Mark Nile | 600 | 200 | Closed
| Migrate Desktop Application | End-user Training | 2021-08-06 | 2021-08-30 | John Watson | 0 | 2000 | Open
| Migrate from Legacy Server | Migrate table structures | 2021-09-04 | 2021-09-29 | John Watson | 0 | 2500 | Pending
| Migrate from Legacy Server | Create new database connection | 2021-07-17 | 2021-08-05 | Scott Spencer | 0 | 100 | Pending
| Migrate from Legacy Server | Implement integration using Oracle | 2021-09-05 | 2021-09-09 | Mark Nile | 0 | 1500 | Pending
| Migrate from Legacy Server | Convert processes | 2021-07-22 | 2021-07-27 | Pam King | 0 | 3000 | Pending
| Migrate from Legacy Server | Decommission SQL Server | 2021-09-13 | 2021-10-05 | Al Bines | 0 | 500 | Pending
| Migrate from Legacy Server | Map data usage | 2021-09-25 | 2021-10-01 | Mark Nile | 0 | 8000 | Pending
| Migrate from Legacy Server | Notify users | 2021-10-08 | 2021-11-06 | Mark Nile | 0 | 200 | Pending
| Migrate from Legacy Server | Identify integration points | 2021-08-01 | 2021-08-29 | Mark Nile | 0 | 2000 | Pending
| Migrate from Legacy Server | Obtain credentials | 2021-10-02 | 2021-10-15 | James Cassidy | 0 | 500 | Pending
| Migrate from Legacy Server | Import data | 2021-10-01 | 2021-10-04 | John Watson | 0 | 1000 | Pending
| Public Website | Check software licenses | 2021-09-19 | 2021-09-27 | Tom Suess | 100 | 100 | Closed
| Public Website | Determine host server | 2021-07-11 | 2021-07-22 | Tiger Scott | 200 | 200 | Closed
| Public Website | Develop web pages | 2021-09-29 | 2021-10-03 | Tiger Scott | 800 | 2000 | On-Hold
| Public Website | Purchase additional software licenses, if needed | 2021-07-15 | 2021-08-10 | Al Bines | 300 | 1000 | On-Hold
| Public Website | Plan rollout schedule | 2021-09-25 | 2021-10-23 | Tom Suess | 120 | 100 | On-Hold
| Software Projects Tracking | Enter base data (Projects, Milestones, etc.) | 2021-07-28 | 2021-08-22 | Tom Suess | 200 | 200 | Closed
| Software Projects Tracking | Load current tasks and enhancements | 2021-08-07 | 2021-08-18 | Tom Suess | 400 | 500 | Closed
| Software Projects Tracking | Conduct project kickoff meeting | 2021-08-27 | 2021-09-05 | Pam King | 100 | 100 | Closed
| Software Projects Tracking | Customize Software Projects software | 2021-07-25 | 2021-08-18 | Tom Suess | 600 | 1000 | Open
| Train Developers | Publish development standards | 2021-09-27 | 2021-10-01 | John Watson | 1000 | 2000 | On-Hold
| Train Developers | Publish links to self-study courses | 2021-07-29 | 2021-08-03 | John Watson | 100 | 100 | Closed
| Train Developers | Create training workspace | 2021-08-24 | 2021-09-11 | James Cassidy | 500 | 700 | Closed
Sum | [5 empty] | 60770
Average | [6 empty] | 1785.6164